## Sheet1
Stage | Activity | Est. Duration | Start date | End date | Deliverables
Research Design and Planning | Finalize research statement | 1 week | 2024-01-05 | 2024-01-21 | Research Proposal
| Feasibility and requirement analysis | 1 week | 2024-01-12 | 2024-01-19 | Requirement Specification
Literature Review | Search and categorize relevant literature | 4 weeks | 2024-01-05 | 2024-02-03 | Reference list
| Prepare draft literature review | 6 weeks | 2024-02-05 | 2024-03-18 | Literature review and analysis
Data Collection | Finalize sampling plan | 2 weeks | 2024-02-12 | 2024-02-26 | Data collection and sampling plan
| Carry out data collection | 4 weeks | 2024-03-01 | 2024-03-28 | Raw data
| Prepare dataset | 1 week | 2024-03-29 | 2024-04-05 | Draft dataset
Data Analysis | Clean and annotate data | 1 week | 2024-04-06 | 2024-04-13 | Preprocessed dataset
| Analyze data behaviour | 1 week | 2024-04-14 | 2024-04-21 | Data analysis report
Speech Processing Model | Decide finer details of the neural network architecture | 2 weeks | 2024-04-22 | 2024-05-05 | Low level design document
| Create prototype of the algorithm | 4 weeks | 2024-06-25 | 2024-07-25 | Proof of concept
| Fine tune the model | 2 weeks | 2024-07-26 | 2024-08-10 | Generative speech enhancement model
| Expand to include multiple scenarios | 4 weeks | 2024-08-11 | 2024-09-11 | Multiagent speech processing model
Paper writing | Draft the findings | 2 weeks | 2024-09-12 | 2024-09-26 | First draft
| Seek feedback from Guide and iteratively improve | 1 week | 2024-09-27 | 2024-10-10 | Final draft
| List conferences, journals and submission details | 1 week | 2024-10-11 | 2024-10-20 | Submission Plan